## Product Backlog
Module | ID | User Stories | Initial | Sprint# | Total | S1 done | S1 rem | S2 done | S2 rem | S3 done | S3 rem | S4 done | S4 rem
User Management | 1.1 | user, create account using name & phone number | 14 | 1 | 60 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Management | 1.2 | user, login using phone number | 8 | 1 | 60 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Management | 1.3 | user, select preferred language | 6 | 1 | 60 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Management | 1.4 | user, view profile & activity history | 12 | 1 | 60 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0
User Management | 1.5 | user, enable offline access | 10 | 1 | 60 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Crop Health Checker | 2.1 | user, capture crop image | 12 | 2 | 85 | 0 | 12 | 8 | 4 | 4 | 0 | 0 | 0
Crop Health Checker | 2.2 | user, upload image (online/offline) | 16 | 2 | 85 | 0 | 16 | 10 | 6 | 6 | 0 | 0 | 0
Crop Health Checker | 2.3 | system, offline image queue handling | 18 | 2 | 85 | 0 | 18 | 12 | 6 | 6 | 0 | 0 | 0
Crop Health Checker | 2.4 | system, AI-based image analysis | 30 | 3 | 95 | 0 | 30 | 0 | 30 | 15 | 15 | 15 | 0
Crop Health Checker | 2.5 | system, show diagnosis & recommendations | 18 | 3 | 95 | 0 | 18 | 0 | 18 | 10 | 8 | 8 | 0
Crop Health Checker | 2.6 | user, view diagnosis history | 10 | 3 | 95 | 0 | 10 | 0 | 10 | 6 | 4 | 4 | 0
Weather Forecast | 3.1 | user, location-based weather data | 14 | 2 | 70 | 0 | 14 | 9 | 5 | 5 | 0 | 0 | 0
Weather Forecast | 3.2 | user, daily & weekly forecast view | 12 | 2 | 70 | 0 | 12 | 8 | 4 | 4 | 0 | 0 | 0
Weather Forecast | 3.3 | system, weather alerts generation | 10 | 3 | 70 | 0 | 10 | 0 | 10 | 6 | 4 | 4 | 0
Weather Forecast | 3.4 | system, send notifications | 10 | 3 | 70 | 0 | 10 | 0 | 10 | 6 | 4 | 4 | 0
Weather Forecast | 3.5 | system, farming advice based on weather | 16 | 4 | 70 | 0 | 16 | 0 | 16 | 0 | 16 | 9 | 7
Crop Library | 4.1 | user, search crops by filter | 14 | 3 | 65 | 0 | 14 | 0 | 14 | 8 | 6 | 6 | 0
Crop Library | 4.2 | user, view crop profiles | 18 | 3 | 65 | 0 | 18 | 0 | 18 | 10 | 8 | 8 | 0
Crop Library | 4.3 | user, save crops offline | 10 | 4 | 65 | 0 | 10 | 0 | 10 | 0 | 10 | 6 | 4
Crop Library | 4.4 | system, manage crop data | 14 | 4 | 65 | 0 | 14 | 0 | 14 | 0 | 14 | 8 | 6
Community Forum | 5.1 | user, create post with image | 16 | 4 | 60 | 0 | 16 | 0 | 16 | 0 | 16 | 9 | 7
Community Forum | 5.2 | user, comment on posts | 10 | 4 | 60 | 0 | 10 | 0 | 10 | 0 | 10 | 6 | 4
Community Forum | 5.3 | user, like posts | 6 | 4 | 60 | 0 | 6 | 0 | 6 | 0 | 6 | 4 | 2
Community Forum | 5.4 | user, search posts by keyword | 12 | 4 | 60 | 0 | 12 | 0 | 12 | 0 | 12 | 7 | 5
Admin System | 6.1 | admin, manage users | 14 | 4 | 60 | 0 | 14 | 0 | 14 | 0 | 14 | 8 | 6
Admin System | 6.2 | admin, monitor logs & activities | 10 | 4 | 60 | 0 | 10 | 0 | 10 | 0 | 10 | 6 | 4
Admin System | 6.3 | system, maintain authentication logs | 10 | 4 | 60 | 0 | 10 | 0 | 10 | 0 | 10 | 5 | 5
|  |  | 350 |  |  | 50 |  | 47 |  | 86 |  | 117

## Spent
| Sprint 1 | [5 empty] | Sprint 2 |  |  |  |  | Sprint 3 |  |  |  |  | Sprint 4
Person | Level | Weight | Allocation | Cost |  | Person | Level | Weight | Allocation | Cost | Person | Level | Weight | Allocation | Cost | Person | Level | Weight | Allocation | Cost
MD. Afridi | Scrum Master | 1.5 | 100% | 1.5 |  | MD. Afridi | Scrum Master | 1.5 | 100% | 1.5 | MD. Afridi | Scrum Master | 1.5 | 75% | 1.125 | MD. Afridi | Scrum Master | 1.5 | 95% | 1.425
Kazi Mazharul Islam Mridul | Junior Developer | 0.9 | 60% | 0.54 |  | Kazi Mazharul Islam Mridul | Junior Developer | 0.9 | 100% | 0.9 | Kazi Mazharul Islam Mridul | Junior Developer | 0.9 | 100% | 0.9 | Kazi Mazharul Islam Mridul | Junior Developer | 0.9 | 100% | 0.9
Md Arman Hossain | Senior Developer | 1.2 | 100% | 1.2 |  | Md Arman Hossain | Senior Developer | 1.2 | 80% | 0.96 | Md Arman Hossain | Senior Developer | 1.2 | 95% | 1.14 | Md Arman Hossain | Senior Developer | 1.2 | 100% | 1.2
Israt Jahan Tasnim | Junior Developer | 0.9 | 90% | 0.81 |  | Israt Jahan Tasnim | Junior Developer | 0.9 | 100% | 0.9 | Israt Jahan Tasnim | Junior Developer | 0.9 | 80% | 0.72 | Israt Jahan Tasnim | Junior Developer | 0.9 | 100% | 0.9
Tasnim Jabir | Senior Developer | 1.2 | 100% | 1.2 |  | Tasnim Jabir | Senior Developer | 1.2 | 100% | 1.2 | Tasnim Jabir | Senior Developer | 1.2 | 60% | 0.72 | Tasnim Jabir | Senior Developer | 1.2 | 50% | 0.6
|  | 5.7 | 450% | 5.25 |  |  |  | 5.7 | 480% | 5.46 |  |  | 5.7 | 410% | 4.605 |  |  | 5.7 | 445% | 5.025
|  | Metric | Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4
|  | Cost in Man Weeks | 5.25 | 5.46 | 4.605 | 5.025
|  | Cost in Man Days | 26.25 | 27.3 | 23.025 | 25.125
|  | Actual Cost Cumulative | 5.25 | 10.71 | 15.315 | 20.34
|  | Earned Value | 14.2857 | 13.4286 | 24.5714 | 33.4286
|  | Cumulative EV | 14.2857 | 27.7143 | 52.2857 | 85.7143
|  | Cost Variance | -11.5255 | -24.9406 | -23.0093 | -14.2857
|  | Planed Value | 14.2857 | 15.4286 | 24.5714 | 45.7143
|  | Cumulative PV | 14.2857 | 29.7143 | 54.2857 | 100 | 20.34
|  | Schedule Variance | 0 | -2 | -2 | -14.2857

## Pivot
Row Labels | Sum of Initial Estimation | Row Labels | Sum of Initial Estimation | Start Date | End Date
1. User Management | 50 | 1 | 92 | 2026-11-01 | 1-31-2026
2. Crop Health Checker | 104 | 2 | 72 | 2026-01-02 | 2-15-2026
3. Weather Forecast | 62 | 3 | 69 | 2-16-26 | 2026-05-03
4. Crop Library | 56 | 4 | 117 | 2026-06-03 | 3-25-2026
5. Community Forum | 44 | Grand Total | 350
6. Admin System | 34
Grand Total | 350